## Product Backlog
SPRINT #2 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
6 | Worker Dashboard | 6.1 | Create appointments table for workers | Shreya |  |  | X
|  | 6.2 | Connect backend to frontend | Shreya
|  | 6.3 | Display worker's appointments on dashboard | Shreya |  | x
|  | 6.4 | Implement bookings backend functions (e.g. get booking) | Anthony |  |  | X
7 | Booking Feature | 7.1 | Connect front to backend | jeremy |  |  | x
|  | 7.2 | Implement backend validation | Anthony |  |  | X
|  | 7.3 | Implement frontend validation | Catherine |  |  | x
9 | Customer checks available services | 9.1 | Implement list that shows available services on booking page | Catherine |  | x
|  | 9.2 | Implement services drop down menu | Catherine |  |  | x
|  | 9.3 | Implement service table | Anthony |  |  | X
24 | Registration for a new customer | 24.1 | Implement registration form | Stephanie |  |  | X
|  | 24.2 | Connect backend to frontend | Stephanie |  |  | X
|  | 24.3 | Implement backend validation | Stephanie |  |  | X
|  | 24.4 | Implement frontend validation | Stephanie |  |  | X
5 | Authentication and Authorisation | 5.1 | Implement authentication for user type | jeremy |  |  | x
|  | 5.2 | Redirect to the appropriate page based on the type of user | jeremy |  |  | x

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #NAME?
| Previous Year | #REF! | #NAME?
| Position | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | Worker Dashboard | #N/A | #N/A | #N/A | #N/A | #N/A
2 |  | #N/A | #N/A | #N/A | #N/A | #N/A
3 |  | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR!
5 | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR!
6 |  | #N/A | #N/A | #N/A | #N/A | #N/A
7 |  | #N/A | #N/A | #N/A | #N/A | #N/A
8 |  | #N/A | #N/A | #N/A | #N/A | #N/A
9 |  | #N/A | #N/A | #N/A | #N/A | #N/A
10 | Booking Feature | #N/A | #N/A | #N/A | #N/A | #N/A
11 |  | #N/A | #N/A | #N/A | #N/A | #N/A
12 |  | #N/A | #N/A | #N/A | #N/A | #N/A
13 |  | #N/A | #N/A | #N/A | #N/A | #N/A
14 |  | #N/A | #N/A | #N/A | #N/A | #N/A
15 |  | #N/A | #N/A | #N/A | #N/A | #N/A
16 |  | #N/A | #N/A | #N/A | #N/A | #N/A
17 |  | #N/A | #N/A | #N/A | #N/A | #N/A
18 |  | #N/A | #N/A | #N/A | #N/A | #N/A
19 |  | #N/A | #N/A | #N/A | #N/A | #N/A
20 |  | #N/A | #N/A | #N/A | #N/A | #N/A
21 | Registration for a new customer | #N/A | #N/A | #N/A | #N/A | #N/A
22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 |  | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A