## Product Backlog
PRODUCT BACKLOG
ID | ITEM | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES
1 | User Home Page Login Feature | Jeremy | High | 5 | Not started | There is a functioning login button on the homepage which will redirect the user to the login page
2 | User Home Page Register Feature | Jeremy | Medium | 5 | Not started | There is a functioning registerations button on the homepage which will redirect the user to the registration page
3 | User Home Page Business Contacts | Shreya | Low | 3 | Not started | There is a functioning button on the homepage which will redirect the user to the business' contacts page
4 | Login Authentication | Anthony | High | 5 | Not started | When a certain type of user logs in they will be redirected to a specfic page for they're user type. Customers will be directed to a booking page, and Workers to their dashboard
5 | Authentication and Authorisation | Catherine | High | 3 | Not started | Only registered customers can access the booking page by logging in through the login feature. Other users will be prompted with a message telling them to register. | Redirect to the correct page. For example customers go to bookings and workers go to dashboard
6 | Worker Dashboard | Anthony | High | 8 | Not started | The workers page displays a dahsboard showing them any bookings customers have made with them.
7 | User Booking Feature | Anthony | High | 5 | Not started | Customers are able to make a booking with the business at a time they have specified
8 | Worker Login | Anthony | Mediun | 3 | Not started | Workers will be redirected to their dashboard page when they login to the website, displaying their appointments.
9 | Customer checks available services | Shreya | High | 8 | Not started | The list of available services is visually appealing, has all relevant information, and passes all tests
10 | Customer views profile details | Shreya | Low | 3 | Not started | Customer can successfully view details, passes all tests and is tested under product environment
11 | Customer edits profile details | Shreya | Low | 5 | Not started | Customer can successfully update details, passes all tests and is permanently updated in database
12 | Admin can check account type | Stephanie | Medium | 5 |  | Admin can view profile that shows account type as 'Admin'
13 | Admin can check all worker’s availability | Stephanie | Low | 8 |  | There is a button on the admin page that will redirect the admin to a page that shows a table of all workers' availability
14 | Admin can add new employee | Stephanie | Low | 8 |  | There is a button on admin page that will redirect the admin to add workers' page that let the admin fill in the worker's information
15 | Admin can add working time for next month | stephanie | Low | 13 |  | There is a button on admin page that will redirect to a form that allows the admin to create a new working time
16 | Admin can edit working time | stephanie | Low | 5 |  | Admin can select a worker and modify their working time
17 | Workers can add their working time | stephanie | Low | 5 |  | There is button in Worker's account page where they can add their working time
18 | Customer cancel appointment | stephanie | Low | 5 |  | There is a cancel button in the appointment page given that the appointment is not in 48 hours
19 | Worker get notification | stephanie | Low | 5 |  | Worker can see the information of the canceled appointment in their dashboard
20 | Customer books service | Catherine | High | 40 | Not started | Customer is able to book an appointment by selecting a service, date, time and worker. The slot is blocked for other customers to make an appointment.
21 | Customer displays history of bookings | Catherine | Medium | 8 | Not started | Customer is able to view all of their past bookings when they click on the past bookings button on their profile page.
22 | Admin views customers' past bookings | Catherine | Medium | 8 | Not started | Admin can view a list of customers who have made an appointment with their service from which they can select one customer and view their past bookings.
23 | Worker can view their own profile | Jeremy | Medium | 3 | Not started | Worker are able to view all data of themselves which retrieve from the database ,all tests were passed successfully
24 | Registration for a new customer | Jeremy | High | 8 | Not started | New customer can successfully create an account by themselves,the information of customer exsist in the database, able to login after the account has been created
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #NAME?
| Previous Year | #REF! | #NAME?
| Position | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | User Home Page Login Feature | #N/A | #N/A | #N/A | #N/A | #N/A
2 | User Home Page Register Feature | #N/A | #N/A | #N/A | #N/A | #N/A
3 | User Home Page Business Contacts | #N/A | #N/A | #N/A | #N/A | #N/A
4 | Login Authentication | #N/A | #N/A | #N/A | #N/A | #N/A
5 | Authentication and Authorisation | #N/A | #N/A | #N/A | #N/A | #N/A
6 | Worker Dashboard | #N/A | #N/A | #N/A | #N/A | #N/A
7 | User Booking Feature | #N/A | #N/A | #N/A | #N/A | #N/A
8 | Worker Login | #N/A | #N/A | #N/A | #N/A | #N/A
9 | Customer checks available services | #N/A | #N/A | #N/A | #N/A | #N/A
10 | Customer views profile details | #N/A | #N/A | #N/A | #N/A | #N/A
11 | Customer edits profile details | #N/A | #N/A | #N/A | #N/A | #N/A
12 | Admin can check account type | #N/A | #N/A | #N/A | #N/A | #N/A
13 | Admin can check all worker’s availability | #N/A | #N/A | #N/A | #N/A | #N/A
14 | Admin can add new employee | #N/A | #N/A | #N/A | #N/A | #N/A
15 | Admin can add working time for next month | #N/A | #N/A | #N/A | #N/A | #N/A
16 | Admin can edit working time | #N/A | #N/A | #N/A | #N/A | #N/A
17 | Workers can add their working time | #N/A | #N/A | #N/A | #N/A | #N/A
18 | Customer cancel appointment | #N/A | #N/A | #N/A | #N/A | #N/A
19 | Worker get notification | #N/A | #N/A | #N/A | #N/A | #N/A
20 | Customer books service | #N/A | #N/A | #N/A | #N/A | #N/A
21 | Customer displays history of bookings | #N/A | #N/A | #N/A | #N/A | #N/A
22 | Admin views customers' past bookings | #N/A | #N/A | #N/A | #N/A | #N/A
23 | Worker can view their own profile | #N/A | #N/A | #N/A | #N/A | #N/A
24 | Registration for a new customer | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A