## Product Backlog
SPRINT #4 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
7 | Booking Feature | 7.1 | Implement frontend validation for date and time | Stephanie | x
|  | 7.2 | Implement services drop down menu | Catherine |  |  | x
|  | 7.3 | Implement worker drop down menu | Catherine |  | x
|  | 7.4 | Re-implement backend validation for booking (i.e. ensure that there is a valid worker and service) | Anthony |  |  | X
9 | Customer checks available services | 9.1 | Implement table that shows available services on booking page | Catherine |  |  | x
24 | Registration for a new customer | 24.1 | Fix phone validation | Stephanie |  | x
25 | View homepage | 25.1 | Create home page | Shreya |  |  | x
|  | 25.2 | Redirect routing to make home page the root page | Shreya |  |  | x
|  | 25.3 | Display available service | Shreya | x

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #NAME?
| Previous Year | #REF! | #NAME?
| Position | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR!
5 | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 |  | #N/A | #N/A | #N/A | #N/A | #N/A
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 |  | #N/A | #N/A | #N/A | #N/A | #N/A
10 | Booking Feature | #N/A | #N/A | #N/A | #N/A | #N/A
11 |  | #N/A | #N/A | #N/A | #N/A | #N/A
12 |  | #N/A | #N/A | #N/A | #N/A | #N/A
13 |  | #N/A | #N/A | #N/A | #N/A | #N/A
14 | View homepage | #N/A | #N/A | #N/A | #N/A | #N/A
15 |  | #N/A | #N/A | #N/A | #N/A | #N/A
16 |  | #N/A | #N/A | #N/A | #N/A | #N/A
17 | Registration for a new customer | #N/A | #N/A | #N/A | #N/A | #N/A
18 |  | #N/A | #N/A | #N/A | #N/A | #N/A
19 |  | #N/A | #N/A | #N/A | #N/A | #N/A
20 |  | #N/A | #N/A | #N/A | #N/A | #N/A
21 |  | #N/A | #N/A | #N/A | #N/A | #N/A
22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 |  | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A