## Product Backlog
SPRINT #1 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
1 | User Home Page Login Feature | 1.1 | Develop basic homepage front end | Jeremy |  |  | x
|  | 1.2 | Implement login button | Jeremy |  |  | x
|  | 1.3 | Develop login page front end | Jeremy |  |  | x
|  | 1.4 | Develop login form | Jeremy |  |  | x
2 | User Home Page Register Feature | 2.1 | Develop register page front end | Jeremy |  |  | x
|  | 2.2 | Develop register form | Stephanie |  |  | x
|  | 2.3 | Implement Register button | Jeremy |  |  | x
3 | User Home Page Business Contacts | 3.1 | Create UI template for business contacts page | Jeremy |  |  | x
|  | 3.2 | Perform routing to direct to this page when the 'Contact' button is clicked | Shreya |  |  | x
|  | 3.3 | Implement 'Contacts' button | Jeremy |  |  | x
4 | Login Authentication | 4.1 | Implement login function | Anthony |  |  | X
|  | 4.2 | Implement authetication for username/password | Anthony |  |  | X
|  | 4.3 | Implement User table/database | Anthony |  |  | X
5 | Authentication and Authorisation | 5.1 | Implement authentication for user type | Catherine |  |  | x
|  | 5.2 | Redirect to the appropriate page based on the type of user | Stephanie |  |  | x
|  | 5.3 | Create basic page for customer | Shreya |  |  | x
|  | 5.4 | Create basic page for worker | Shreya |  |  | x
|  | 5.5 | Create basic page for admin | Shreya |  |  | x
7 | User Booking Feature | 7.1 | Implement booking page | Shreya |  |  | x
|  | 7.2 | Implement booking field (i.e date, time) | Stephanie |  |  | x
|  | 7.3 | Implement confirmation message/pop up | Catherine |  |  | x
|  | 7.4 | Booking table/database | Anthony |  |  | X

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #NAME?
| Previous Year | #REF! | #NAME?
| Position | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | User Home Page Login Feature | #N/A | #N/A | #N/A | #N/A | #N/A
2 |  | #N/A | #N/A | #N/A | #N/A | #N/A
3 |  | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR!
5 | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR!
6 |  | #N/A | #N/A | #N/A | #N/A | #N/A
7 | User Home Page Register Feature | #N/A | #N/A | #N/A | #N/A | #N/A
8 |  | #N/A | #N/A | #N/A | #N/A | #N/A
9 |  | #N/A | #N/A | #N/A | #N/A | #N/A
10 |  | #N/A | #N/A | #N/A | #N/A | #N/A
11 | User Home Page Business Contacts | #N/A | #N/A | #N/A | #N/A | #N/A
12 |  | #N/A | #N/A | #N/A | #N/A | #N/A
13 |  | #N/A | #N/A | #N/A | #N/A | #N/A
14 |  | #N/A | #N/A | #N/A | #N/A | #N/A
15 | Login Authentication | #N/A | #N/A | #N/A | #N/A | #N/A
16 |  | #N/A | #N/A | #N/A | #N/A | #N/A
17 | Authentication and Authorisation | #N/A | #N/A | #N/A | #N/A | #N/A
18 |  | #N/A | #N/A | #N/A | #N/A | #N/A
19 | User Booking Feature | #N/A | #N/A | #N/A | #N/A | #N/A
20 |  | #N/A | #N/A | #N/A | #N/A | #N/A
21 |  | #N/A | #N/A | #N/A | #N/A | #N/A
22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 |  | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A